## Asset Renewals & Maintenance
Sample Renewals and Maintenance Plan
Notes
(1). The tables below are a guide only and we recommend that you get timely quotes from professionals for each task. (2). The 'today cost' column is an estimate only and is a guide to help you budget. (3). Use the quote column to keep a record of quotes for your renewals & maintenance over the years. It will help you in times to come. (4). The priority column is our recommendation on when you should complete the renewal or maintenace task. It is based on Ren and Age. (5). Ren is the last time the asset was renewed, improved or maintained. Or when it was built. (6). The years column is a useful planning tool so you can schedule your renewals and maintenance accurately and effectively.
Estimated Asset Renewal Cost | 1566000
Assets - Detailed | Today Cost | Quote | Priority | Category | Locale | Structure | Type | Area (sq.m) | Ren | Age (yrs) | Notes | Mulitplier
Club House | 960000 |  | As Required | Buildings | Club House | Concrete Block/Timber | Single Level | 320 | 1977 | 45 | Box type single level club house with bar kitchen. Exterior requires painting | 3000
Club House Roof | 48000 |  | Medium | Buildings | Club House | Iron | Pitched | 320 | 1977 | 45 | Shallow angle pitched roof. Requires replacement in next 5-10 years. | 150
Club House Bar/Kitchen | 24000 |  | Medium | Club Assets | Club House | Timber | Fit Out | 16 | 2005 | 17 | Home style kitchen with no extraction. Bar fridge, no beer taps. No chiller. | 1500
Change Room - Male | 144000 |  | Medium | Buildings | Club House | Timber | Male | 36 | 1977 | 45 | Open shower block. 1x Urinal, 1x flush toilet. | 4000
Change Room - Female | 120000 |  | High | Buildings | Club House | Timber | Female | 30 | 1977 | 45 | 2x shower cubicles with curtains. 2x flush toilets. | 4000
Green 1 (Carpet) | 250000 |  | Medium | Sports Assets |  | Carpet | Playing surface | 625.6 | 2012 | 10 | Individual green cost based on current footprint and includes perimeter areas. | 45
Green 2 (Natural) | 0 |  | Medium | Sports Assets |  | Natural | Playing surface | 625.6 | 2012 | 10 | Individual green cost based on current footprint and includes perimeter areas. | 45
Green 3 (Natural) | 0 |  | High | Sports Assets |  | Natural | Playing surface | 625.6 | 2005 | 17 | Individual green cost based on current footprint and includes perimeter areas. | 45
Green Equiptment | 10000 |  | Low | Club Assets | Shed |  | Various |  | 2017 | 5 | Mower, roller, sprayer, etc.. - assets grouped
Furniture/Equipment | 10000 |  | Low | Club Assets | All | Various | Various | 1 | 2012 | 10 | Includes AED, cleaning equipment, Bowls Timer - assets grouped | 16000
Estimated Annual Maintenance Cost | 32830
Assets - Detailed | Today Cost | Quote | Maintain Cycle | Category | Task | Structure | Type | Area (sq.m) | Ren | Age | Notes
Club House | 640 |  | Annual | Buildings | Wash | Concrete Block/Timber | Exterior | 320 | 1977 | 45 | Exterior annual building wash. Make repairs as required. | 2
Club House | 4000 |  | Annual | Buildings | Paint & Repair | Timber/Gib Board | Interior | 32 | 1977 | 45 | Set an annual budget for this & target high use areas. Recommend a professional painter. | 125
Club House Roof | 800 |  | Annual | Buildings | Wash | Iron | Pitched | 320 | 1977 | 45 | Exterior annual roof wash. Make repairs as required. Complete with building wash. Paint if required. NB - working at height (H&S). | 2.5
Club House Bar/Kitchen | 160 |  | Annual | Club Assets | Deep Clean | Timber | Fit Out | 16 | 2005 | 17 | Deep clean for high use areas. A kitchen hygiene rating maybe required to comply with. | 10
Change Room - Male | 180 |  | Annual | Buildings | Deep Clean | Timber | Male | 36 | 1977 | 45 | Deep clean for high use areas. Schedule this outside of regular clean cycle | 5
Change Room - Female | 150 |  | Annual | Buildings | Deep Clean | Timber | Female | 30 | 1977 | 45 | Deep clean for high use areas. Schedule this outside of regular clean cycle | 5
Green 1 (Carpet) | 2400 |  | Annual | Sports Assets | Maintain | Carpet | Playing Surface | 625.6 | 2012 | 10 | Complete reg maintenance of carpet green. Recommend a professional green keeper | 0.55
Green 2 (Natural) | 12000 |  | Annual | Sports Assets | Maintain | Natural Green | Playing Surface | 625.6 | 2012 | 10 | Complete reg maintenance of green - spraying, weeding etc... Recommend a professional green keeper | 0.55
Green 3 (Natural) | 12000 |  | Annual | Sports Assets | Maintain | Natural Green | Playing Surface | 625.6 | 2012 | 10 | Complete reg maintenance of green - spraying, weeding etc... Recommend a professional green keeper | 0.55
Green Equiptment | 500 |  | Annual | Club Assets | Maintain |  | Various | 2 | 2017 | 5 | Includes all equipment that is to do with maintaining greens & set aside an annual budget | 135
Furniture/Equipment | 500 |  | Annual | Club Assets | Repair | All | Various | 1 | 2012 | 10 | Includes all equipment that isnt to do with above line & set aside an annual budget | 500
Estimated Long Term Maintenance Cost | 302661
Assets - Detailed | Today Cost | Quote | Maintain Cycle | Category | Task | Structure | Type | Area (sq.m) | Ren | Age | Notes
Club House | 52661 |  | Low (10) | Buildings | Paint & Repair | Concrete Block/Timber | Exterior | 320 | 1977 | 45 | Recommended 10 year paint for cladding. Make repairs as required
Green Replacement | 250000 |  | Low (10) | Sports Assets | Replace Carpet | Stainless Steel, Carpet | Mobile | 14 | 2020 | 2 | Replace carpet. Assume at 10 years
These items are estimated to cost as above in 10 years.